## Data
Theme | Objective | Project/s Ref | Responsibility | HS&W Lead | Measure | Detailed action | Who | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | RAGB
Theme 1 - Leadership | Promote a behavioral safety culture through innovation and continuous improvement | 1,5,9,16,27,47,53,64,69 | Managers | Risk Lead- LB | Increased number of risk led projects based on continuous improvement. | Trending information provided to HS&W Policy Group to help identify projects, Manufacturing and DTS and ODT to reduce risk assessments. Link to top 11 risks. | LB | Number monitored | Increase by 10% | Increase by 10% | Increase by 10% | Increase by 10% | Green
| Supporting plans to develop our safety and wellbeing | 3,8,10,11,13,14,17,18,19,50,54,73,74,75 Details in High Level Tracker (will move to sharepoint in future) G:\005 Human Resources\004 Health and Safety\001 Everyone\Strategy & Plan\strategy 2018-2023\180614 High Level Project Tracker.xls | Leaders | Project Lead- CS | Projects plans monitored quarterly and status reported to the Policy Group quarterly using RAG status in project tracker. Directorate HS&W plans monitored quarterly at Policy Group with Directorate HS&W co-ordinators. Proactive, forward-thinking approach to prevent harm before it happens. | Directorate plans being developed. Project plan developed. | CS / FS /PT | Plans developed | Plans monitored | Plans monitored | Plans monitored | Plans monitored | Green
| Monitoring accidents and near misses and act on our findings |  | Managers | Improvement Lead-RC | Lessons learned- Accidents/Incidents/Near miss, litigation monitored and reported monthly to Directorates. | CPC and SMT slide for lessons learned, RC provided lessons learned report including litigation lessons. Reported through to Policy Group Quarterly. Audits included. Lessons learned table in all accident reports. | RC | Reported provided quarterly | Reported provided quarterly | Reported provided quarterly | Reported provided quarterly | Reported provided quarterly | Green
| Health, Safety and Wellbeing high visibility and business as usual |  | Managers | PT- CS-FS | Lost time accidents monitored and reported monthly to the Executive Team. SMT member visit departments who have had a level 1 incident to discuss Safety. Named Board member championing Health and Wellbeing as a proactive measure to support colleagues. | Katherine Robinson named board member. Level 1 incident included in BD HS&W scorecard and done in manu/ testing HS. | CS / FS /PT / RC | Reported provided monthly | Reported provided monthly | Reported provided monthly | Reported provided monthly | Reported provided monthly | Green
| Regularly visiting departments and use human factors safety techniques | 25,30,58 | Managers | Risk Lead- LB | Monthly Risk based Awareness campaigns using observations. | Review HSW topics and get them into the same format which will include an observation record sheet. Promote topics through CPC reports. Identify other media for promotion such as BD facebook pages, Weekly ops updates. TBO projects where identified for depts done by local advisor. | LB | Monthly campaign provided | Monthly campaign provided | Monthly campaign provided | Monthly campaign provided | Monthly campaign provided | Green
| Peer to peer use human factors safety techniques | 4,15,47,58 | Managers | improvement Lead-RC | Peer to Peer observations for manual handling refresher and peer to peer observation tool developed and implemented. | Development of tools and aides to support this, visual aides and observation sheets. Referred to in Manual Handling training provision specification. | RC/LB | Peer to peer tool developed | Peer to peer tool implemented | Review | Review | Review | Green
| Working closely with other business support areas and directorates e.g. QA, Corporate Risk, Continuous Improvement, Clinical and Business Continuity |  | QA, Corporate Risk, Continuous Improvement, Clinical and Business Continuity | PT- CS-FS | Directorates HS&W coordinators to engage with outside partners in carrying out HS&W benchmarking. Achieve benchmarking level in comparison with private sector organisations. Stakeholders from other business support areas identified in any HS&W project plans. | BD Coordinator agreed to identify and visit an outside partner for benchmarking- FS JMoore linking with Sainsburys benchmarking on rates. Engagement with natcom and ask them to go out too and reporting back to them. | PT/ CS/ FS | 2 benchmark visits by partners | 2 benchmark visits by partners | 2 benchmark visits by partners | 2 benchmark visits by partners | 2 benchmark visits by partners | Green
| Benchmark safety and wellbeing practices with outside organisations |  | H&S Co-ordinators | PT- CS-FS | H&S co-ordinators to visit a private company to learn from their HS&W system Benchmark againts external organisations using industry standard metrics/meausrements. | BD Coordinator agreed to identify and visit an outside partner for benchmarking | PT/ CS/ FS | 3 benchmark visits by coordinators | 3 benchmark visits by coordinators | 3 benchmark visits by coordinators | 3 benchmark visits by coordinators | 3 benchmark visits by coordinators | Green
| Provide resources and wellbeing for safety development | 27,32,34,44,56 | Managers | Assurance Lead- DP - CS | All departments to have access to assessors and H&W champions and provide them with facility time to promote HS&W. Improve training available for managers in supporting health and wellbeing of colleagues, inc mental health, and 'soft skills'. Review of HS&W systems (accident and risk assessment systems). | Implement mental health awareness packages on Shine. Work with OWD on including 'soft skills' in other training packages. Mental health Wellbeing train the trainer. Implementation of new accident and risk system. | CS / EB | 60% access to champion | 70% | 80% | 90% | 90% | Green
| Working with communities to improve wellbeing links | 36,63 | Managers | All advisors | Local H&W plans in place for each centre, linking with services in the local community | Need for Wellbeing Champion to be identified for each centre to lead on this | Local Advisors | Plan developed for each centre | Audited | Review | Review | Review | Green
| Working to engage colleagues at all levels | 52 | Managers | All advisors | Our voice score. | MW on project group and looking to include ones on wellbeing and possibly stress | MW | Preparation for 2019 | Increase by 10% | preparation for 2020 | Increase by 10% | review | Green
| Working with contractors through estates and facilities | 7,24 | E&F | Risk Lead- LB | Risk led and learning from incidents. Working with procurement to encourage use of health, safety and wellbeing considerate third party contractors. | Review Contractor incidents, identify lead for this from procurement, arrange meeting to outline concerns and look at tendering process | LB | Implementation of contractor monitoring system | No contractor workplace accidents | No contractor workplace accidents | No contractor workplace accidents | No contractor workplace accidents | Green
Theme 2- Safety Culture moving to Prevention culture | Effectively managing health and Wellbeing risks | 5, 9,20 | Managers | Risk Lead-LB | Reduction in all accidents 10% annually, with long term aim of zero harm. Each directorate has a HS&W targets to meet. Managers complete monthly observations from the HSW topics list. Monthly safety inspections / tours / gemba walks completed and recorded on Datix and scorecards Reduction in number of litigation cases. Use of the health needs assessment tool to identify and monitor any health risks. | Monthly trending reports to be circulated through SMT reporting and other reports. Targeted or subject specific audits linked to top 11 eleven risks and any other trends identified. | LB | 10% reduction | 10% reduction | 10% reduction | 10% reduction | 10% reduction | Red
| Monitoring the increase of near miss reporting |  | Managers | Risk Lead-LB | 10% increase in Minor and insignificant injury/ Near miss reporting. | Monthly trending reports to be circulated through SMT reporting and other reports. Scorecard development for | LB | 10% increase | 10% increase | 10% increase | 10% increase | 10% increase | Amber
| Reducing serious incidents | 65 | Managers | Improvement Lead-RC | Reduce costs from incidents and claims. 10% decrease in Level 1-3 incidents. | Quarterly report at Policy Group including numbers and costs from claims. Claims reviewed with Directors after closure. | RC | 10% reduction | 10% reduction | 10% reduction | 10% reduction | 10% reduction | Amber
| Maintaining Health, Safety and Wellbeing mandatory training within the compliance target | 4,15, 48 | Managers | Assurance Lead-DP | 95% Mandatory training compliance. Use of Digital/Media technology for mandatory training. | Circulated to SMT, Natcom, by centre and package. | LB / Advisors | 95% | 95% | 95% | 95% | 95% | Green
| Adopting a just culture approach in accidents/incidents root cause analysis | 25, 58 | Managers | All Advisors | Develop and engage with Human Factors group to prioritise and share learning with colleagues and stakeholders. | Work with managers and HR to look at the just culture flow chart to assist with RCA and actions to be taken | PT | Attend meetings | Attend meetings | Attend meetings | Attend meetings | Attend meetings | Green
| Consistently utilise the Human Factors principles in Root Cause analysis | 5, 9,10,22,29,57,62, 64,67, 69,71 | Managers | All advisors & Assurance Lead-DP | Simplify and reduce the number of risk assessments and HS&W documents by 20% of the period of the strategy. 100% of Level 1-2 incidents have Root cause analysis completed using the analysis of behaviour flowcharts. Measured by attaching flow chart to investigation report. | DTS project, COSHH cleaning projects and manufacturing managers. | LB/DP | Identify documents to be replaced. 100% RCA | 10% reduction. 100% RCA | 5% reduction. 100% RCA | 5% reduction. 100% RCA | review. 100% RCA | Green
| Encouraging peer to peer safety observations using human factors | 12, 45, 47 | Managers | Assurance Lead-DP | Development of aids to support this including use of digital/media technology. | NA observation tool DP to pick up and plan in implementation. LB manual handling observations cards in BD. | DP / LB | Develop tool | Implement | review | review | review | Amber
| Managers/Leaders to encourage personal responsibility and accountability for safety and wellbeing to be developed | 4,6,15,48,51,56 | Managers | Improvement Lead- RC | Enhancement of the Human Factors approach to Safety and Wellbeing for all colleagues. Improve training available for managers in supporting health and wellbeing of colleagues, inc mental health, and 'soft skills'. New training courses developed for additional non mandatory training. Data from Datix with person causes identified as a root cause in incidents. | New courses developed based on trends/themes/risk such as Mental Health. Standard H&S packages reviewed on a regular basis to ensure content includes consistent message across levels and up to date best practice | RC and BAU? | New training courses developed | New training courses implemented | review | review | review | Green
| Managers/Leaders to encourage incident and near miss reporting |  | Managers | Improvement Lead- RC | Enhancement of the Human Factors approach to Safety and Wellbeing for all colleague to be part of the Leadership/Management ladder training. | In the leadership ladder in level 1, observation approach. Level 2 safety culture and 3 leadership not agreed yet. | FS | In ladder | review | review | review | review | Green
| Managers/Leaders to investigate all injuries and incidents and understand the causes to identify lessons learned |  | Managers H&S Co-ordinators | Risk Lead-LB | Risk assessment reviews and actions monitored at management level, reviewed at directorate level. 100% Risk Assessments that are no longer relevant are archived in Datix. All monitoring of this is led by HS&W coordinators monthly. | Monthly trending reports to be circulated through SMT reporting and other reports. Scorecard development for | LB | 100% | 100% | 100% | 100% | 100% | Green
| Managers/Leaders to complete all Corrective and Preventative Action (CAPA) and communicate lessons learned |  | Managers H&S Co-ordinators | Risk Lead-LB | Risk assessment reviews and actions monitored at directorate level and led by HS&W coordinators monthly. Self audits carried out by directorates annually in addition to HS&W dpeartment audit programme. | Out of date risk reporting completed for SMT report. Discuss with CC potential to get out of date risk report set up as a my reports for use by whole HSW team. Set up report on Datix and also make available to managers | LB | 95% and one self audit per directorate | 95% and 7 centre per directorate self audits | 95% and all centres per directorate self audits | 95% and all centres per directorate self audits | 95% and all centres per directorate self audits | Green
| Colleagues to engage in identifying best practice and report near misses |  | All | All advisors &Improvement Lead- RC | Use of praise cards. | Introduce via future HS&W plans. FS to find out about and feedback. | FS | H&S included | review | review | review | review | Green
| Colleagues to take responsibility for their own safety and wellbeing | 12,36 | All | All advisors &Improvement Lead- RC | Quarterly increase in level 4 reporting. Use of peer to peer observations. Increased participation in wellbeing activities. Encourage personal responsibility for own H&W using wellbeing promotions and signposting. | Reporting monitored monthly in SMT report and quarterly at Policy group. Observations monitored via scorecards and local audits. | RC / | Review | review | review | review | review | Green
| Colleagues to follow safe systems of work wherever possible | 21, 47 | All | Assurance Lead-DP | Certification to OHSAS180001/ISO45001 no minor / major non conformances, or observations regarding safe systems of work. | Gaps been identified, audit schedule internal and external. Training auditors course for this year and next. | DP | no major minor observations for SSW | no major minor observations for SSW | no major minor observations for SSW | no major minor observations for SSW | no major minor observations for SSW | Green
Theme 3- Wellbeing | Encouraging usage of targeted wellbeing initiatives | 26,30,32,33,37,41,44,46,52,61,70 | All | All advisors & Wellbeing Support- EB&MW | Completion of observations using H&W topics. Improvement in scores from Britain's Healthiest Workplace Survey. Flu vaccination target 60% front line colleagues. Improved use of physiotherapy and EAP services. Use of mental health wellbeing champions across NHSBT. Increased delivery of resilience courses. | Implement wellbeing initiatives (using Centre Wellbeing Plans) to support the findings from Britain's Healthiest Workplace survey 2017. Improve access to the flu vaccine - improved and targetted communication messaging, online appointment booking, online consent forms. Improved communication of the benefits of using physiotherapy and EAP. More personal stories of colleagues who have used physio and EAP. Continued communication regarding mental health wellbeing champions and increasing visibility across all centres. Monitoring use of MHWC. Further MHWC training dates across NHSBT. Training of new Lighten Up Facilitators. Development of in-house programme with OWD. | All | 60% flu vac target. Increase in wellbeing use | Improvement in britain's healthiest company score | Increase in wellbeing use | Improvement in britain's healthiest company score | Increase in wellbeing use | Green
| Evaluating the wellbeing initiatives | 28,31,38,52,59 | All | All advisors & Wellbeing Support- EB&MW | Reduction in sickness absence as a result of occupational health reasons. Use of health needs assessment tool. Increase in Our Voice score "My organisation takes positive action on health and wellbeing". Increase in opinion survey "I feel safe and secure in my working environment" scores. Reduction in obesity and smoking and increase in physical activity across NHSBT. OH standard group review of initiatives with members giving feedback on implementation. Improvement in scores for colleagues who say they are disabled on 'Our Voice' survey. | Develop Health Needs Assessment Tool. Monitoring of results of repeated Britain's Healthiest Workplace Survey against 2017 survey. Compare results of future 'Our Voice' survey against 2016 'Your Voice' for colleagues with disabilities. Review 'Our Voice' survey results against 2016 'Your Voice' for all colleagues. Review sickness absence figures. | EB /MW | Reduction in work related sickness absence 1.5 OSHA | Reduction in work related sickness absence 1.4 OSHA | Reduction in work related sickness absence 1.3 OSHA | Reduction in work related sickness absence 1.2 OSHA | Reduction in work related sickness absence 1.1 OSHA | Green
| Organising plans for mental wellbeing | 35,36,37,63 | Leaders | Wellbeing support- EB & MW | Mental health promotions supported at local centres / BD teams and included in their Health, Safety and Wellbeing Plans. Mental Health Policy in place. | Work with Mental Health Wellbeing Champions, Disability Health Promotion Advocates and Health and Wellbeing Links to promote mental health initiatives in their local areas. Local Health and Wellbeing Links to regularly attend CPC meetings to raise awareness with management teams. Mental Health Policy to be implemented and awareness raised in all areas. | EB | Promotion per centre BD teams | Promotion per centre BD teams | Promotion per centre BD teams | Promotion per centre BD teams | Promotion per centre BD teams | Green
| Reviewing wellbeing data alongside sickness absence. | 61, 65,70 | Leaders | All advisors & Wellbeing Support- EB&MW | Reduction in sickness absence as a result of occupational health and mental health reasons. Monitoring sickness absence against inequality characteristics (i.e. disability, age, gender, shift patterns, staff grade, etc). Monitoring mental wellbeing data against inequality characteristics. Encouraging colleagues to update their information in ESR. | Review sickness absence figures and mental wellbeing data against inequality characteristics. Communications plan to encourage updating of ESR for disability etc. | EB / LB / CS | Review | Review | Review | Review | review | Amber
| Clearly communicating HS&W requirements and expectations to our colleagues | 39,41 | Managers | Wellbeing support- EB & MW | Increase in use of Musculoskeletal-Physiotherapy. Increase in use of work related stress management tools in People First. All workplace adjustments captured appropriately, reduction in numbers of employees on restrictions or reasonable adjustments. Encourage personal responsibility for own H&W using health promotions and signposting. | Communications plan to raise awareness of rapid access physiotherapy service. Monitoring number of clicks to work related stress pages on People First. Monitoring number of clicks to tailored adjustment agreement reporting tool, and also numbers of adjustments and adjustment reviews input into tool. Work with HR colleagues to ensure they are signposting managers to the tool. Comms relaunch of Mental Health and Wellbeing Policies when reviewed and live. | MW | 10% increase in tailored adjustment agreements | 10% increase in tailored adjustment agreements | 10% increase in tailored adjustment agreements | 10% increase in tailored adjustment agreements | 10% increase in tailored adjustment agreements | Green
| Developing communications plans supporting local needs | 39 | Leaders | All advisors & Wellbeing Support- EB&MW | Musculoskeletal - Physiotherapy interventions provided to colleagues with return to work. Local H&W plans at least at centre level. | Work with HR colleagues / HSW team to ensure that the availability of rapid access physiotherapy is signposted to managers as soon as possible when colleagues report MSK issues. | MW | Local plan | Local plan | Local plan | Local plan | Local plan | Green
| Participating in mental health campaigns | 44 | All | All advisors & Wellbeing Support- EB&MW | Mental Health proactive intervention processes. Increase in number of Mental Health and Wellbeing Champions (MHWC) reduction in mental health absence from work. Signing 'Time to Change' Pledge. Increased numbers of colleague blogs and personal stories. | Monitor numbers of interventions by MHWC. Monitor sickness absence for mental health reasons. Run further MHWC training across NHSBT to fill gaps. Sign 'Time to Change' pledge and communicate this widely. Encourage more personal stories / blogs using health and wellbeing networks and HS&W team. | EB | Increase participation | Increase participation | Increase participation | Increase participation | Increase participation | Green
| Developing and encouraging Mental Health and Wellbeing champions. | 32 | Managers | All advisors & Wellbeing Support- EB&MW | Health and Wellbeing Champions to be developed in all areas of the organisation. Increase in numbers of champions. Increase in reported usage of MHWC by colleagues. | Run further MHWC training courses to fill gaps. Continue to encourage MHWC to run campaigns locally and raise awareness of mental health in their spheres of influence. Monitor usage of MHWC as an intervention. | EB | Increase in numbers | Increase in numbers | Maintain numbers | Maintain numbers | Maintain numbers | Green
| Contributing to local health and wellbeing plans | 36 | All | All advisors & Wellbeing Support- EB&MW | Health, Safety & Wellbeing promotions locally supported at centres and on BD teams, not run centrally by HS&W, clear ownership at CPC with identified local lead. | Encourage health and wellbeing links to add local initiatives to their local H&W plan through CPC meetings. Local H&W lead identified at each centre and linked with EB. | All | Local involvement | Local involvement | Local involvement | Local involvement | Local involvement | Green
| Participating in wellbeing activities where possible | 36 | All | all advisors & Wellbeing Support- EB&MW | Numbers participating in wellbeing activity increase year on year. | Monitoring of local H&W plans. Feedback through HS&W of numbers of colleagues taking part. Feedback / evaluation form for H&W activities. | EB/MW | Increase participation | Increase participation | Increase participation | Increase participation | Increase participation | Green
| Providing feedback on work activities that affect their health | 46 | All | All advisors & Wellbeing Support- EB&MW | Review of the local HS&W plans at CPC's. Quarterly reviews of OHW data from OH provider. Use of health needs assessment tool. | Develop Health Needs Assessment tool. Review OHW data from OH provider. Review H&W plans with CPCs and HSW team. | EB/MW | CPC review | CPC review | CPC review | CPC review | CPC review | Green
Theme 4- Engagement/Influence/ Communication | Completing formal observations and communicate outcomes to colleagues | 23 | Managers | Improvement Lead- RC | Reports to Board, GAC, Exec team, CPC reports using one database. | Monthly lessons to note in CPC report, quarterly report to Policy group and SMT's in future. | RC | Monthly report | Monthly report | Monthly report | Monthly report | Monthly report | Green
| Individually coaching colleagues where appropriate |  | Managers | Improvement Lead- RC | Information on Connect, social media, teamtalk. Link to PDPR process and manager skills. | Regular updates with internal comms on identifying most appropriate and available communication channels to give messages to staff around HS&W | RC | Info available | Info available | Info available | Info available | Info available | Green
| Ensuring interventions are accessible for all colleagues | 44 | Managers | Wellbeing Support-EB & MW | Health, Safety & Wellbeing promotions supported at local centres and included in their Health, Safety and Wellbeing Plans. Information in Connect, teamtalk, social media on interventions that are available for all staff. More focus groups to increase confidence to talk and encourage local support networks. Use of health needs assessment tool to ensure that we understand the wellbeing needs of our colleagues. Clear key messages which use a comms channel to suit the different audiences, inc disability needs. | Communications plan to raise awareness of all interventions available at NHSBT through all the relevant channels - Connect online / magazine / team talk / BD team time / Inside NHSBT / People First news / social media. Signposting to People First pages. Additional PF pages developed where necessary. Develop Health Needs Assessment tool to get baseline of needs of workforce. Look at clear messaging for colleagues with disabilities. Run more focus groups on mental health / wellbeing, etc | RC / PT | Info available | Info available | Info available | Info available | Info available | Green
| Sharing safety and wellbeing stories |  | Managers | Improvement Lead- RC | Information in centres and CPC's reports. Days since last accident. Stories/blogs in connect and other communication channels. Increased use of video blogs. More focus groups to increase confidence to talk and encourage local support networks. | Run more focus groups on mental health / wellbeing to encourage commuication with local colleagues and setting up support networks. Encourage sharing of personal wellbeing stories through blogs etc. Access to regular space in Connect magazine agreed. Days since last accident available in monthly reports via CPC. Details of any local focus or support groups covered in Centre or Directorate HS&W plans | RC | Review | review | review | review | review | Green
| Providing suggestions for improvement |  | All | Risk Lead - LB | Quarterly meetings of the national HS&W committee chaired by BD Director to analyse and monitor progress and agree on future policies. Local HSW committees in place at every main centre. Working with HR colleagues to look at improving the sickness absence monitoring process, esp for colleagues with disabilities or mental health issues. | HSW committee meetings. Project with HR | LB | Review by committee | Review by committee | Review by committee | Review by committee | Review by committee | Green
| Engaging in a learning organisation culture by sharing best practice | 60,62,66 | All | All advisors & assurance Lead-DP | Information in centres of number of days since the last lost time accident. Lessons learned communicated at Policy Group to Directorate co-ordinators and via stories in Connect or other communication channels. Use of safety alerts/bulletins. Regular updates to NHSBT on progress and good news stories. Development of learning organisation with other partners (QA/CI/Gov) | Project on learning organisation. Date of last accident. People first page. | RC /FS | System developed | Implemented | Review | rewview | review | Green
| Union colleagues to work in partnership to achieve this strategy through local and national HS&W committees. | 43, 60 | Union colleagues | Risk Lead - LB | Involvement of our Union Colleagues in inspections and wellbeing campaigns. Attendance at HSW committees. Involving union colleagues in mental health wellbeing champion training. | HSW committee meetings. Project with Union colleagues looking at inspections. Work with Wellbeing to include Union colleagues as Wellbeing champions | LB | Review by committee | Review by committee | Review by committee | Review by committee | Review by committee | Amber